## Sheet1
App | PLA | Iteration | Prod/Non-Prod | Server Data Gathering Due | Solution Design Scheduled | Firewall Request Due | Change Requests Due | Migration Date | Solution Design Due | Testing Completed | Hypercare | Meeting Invite Sent? | Comments
DBD Genes Database | Del Pilar, Jayson | 1 | Non-Prod |  |  |  |  | 2022-10-26 | 2022-10-06 |  |  | Y
ADMI Screener | Del Pilar, Jayson | 1 | Non-Prod |  |  |  |  | 2022-10-26 | 2022-10-06 |  |  | Y
RateManager | Romberger, Scott | 1 | Non-Prod |  | 10/06/2022 06:00 | 2022-10-20 |  | 2022-10-28 | 2022-10-10 |  |  | Y
Altimeter | Jackson, Andy | 2 | Prod |  | 10/11/2022 06:00 | 2022-10-25 | 10/25/2022 | 2022-11-04 | 2022-10-17 |  |  | Y
eNICQ | Randy Overly | 2 | Prod |  | 10/13/2022 08:00 | 2022-10-27 | 10/27/2022 | 2022-11-04 | 2022-10-17 |  |  | Y
EssetteSuite | Reed, William J | 2 | Non-Prod |  | 10/11/2022 10:00 | 2022-10-25 |  | 2022-11-09 | 2022-10-20 |  |  | Y
Salesforce Services | Benninger, Kirsten | 2 | Prod |  | 10/18/2022 06:00 | 2022-11-01 | 11/01/2022 | 2022-11-11 | 2022-10-24 |  |  | Y
Pevco Tube System | Lashock, Stanley R | 2 | Prod |  |  |  |  | 2022-11-11 | 2022-10-24 |  |  | Y
Tableau Server | Schultz, David B | 2 | Prod |  | 10/17/2022 11:00 | 2022-10-31 | 10/31/2022 | 2022-11-11 | 2022-10-24 |  |  | Y
SDS E-Business Server | Britton, Shawn P | 3 | Non-Prod |  | 10/19/2022 11:00 | 2022-11-02 |  | 2022-11-14 | 2022-10-25 |  |  | Y
Serv-U MFT Server | Britton, Shawn P | 3 | Non-Prod |  | 10/19/2022 11:00 | 2022-11-02 |  | 2022-11-14 | 2022-10-25 |  |  | Y
TransSend | Wakeman, Bradley D | 3 | Non-Prod |  | 10/20/2022 11:00 | 2022-11-03 |  | 2022-11-14 | 2022-10-25 |  |  | Y
ACL Suites | Jones, Melissa M | 3 | Prod |  | 10/27/2022 06:00 | 2022-11-10 | 11/10/2022 | 2022-11-18 | 2022-10-31 |  |  | Y
MedInsight | Romberger, Scott | 3 | Prod |  | 10/06/2022 06:00 | 2022-10-20 | 10/20/2022 | 2022-11-18 | 2022-10-31 |  |  | Y
OmniPro-I'mRT | Girardi, Deirdre | 4 | Prod |  | 10/25/2022 11:00 | 2022-11-08 | 11/08/2022 | 2022-12-02 | 2022-11-14 |  |  | Y
Maestro | Girardi, Deirdre | 4 | Prod |  | 10/25/2022 11:00 | 2022-11-08 | 11/08/2022 | 2022-12-02 | 2022-11-14 |  |  | Y
Live Capture | Dietterick, Patricia A | 4 | Prod |  | 11/10/2022 06:00 | 2022-11-24 | 11/24/2022 | 2022-12-08 | 2022-11-18 |  |  | Y
ECHO | Hock, Timothy L | 4 | Prod |  | 11/14/2022 11:00 | 2022-11-28 | 11/28/2022 | 2022-12-09 | 2022-11-21 | 09/07/2022 |  | Y
OutSystems Platform | Shetty, Savitha | 4 | Prod |  | 11/15/2022 07:00 | 2022-11-29 | 11/29/2022 | 2022-12-09 | 2022-11-21 |  |  | Check w/ Saridha
Tower Web Viewer | Reed, William J | 4 | Prod |  | 11/15/2022 07:00 | 2022-11-29 | 11/29/2022 | 2022-12-09 | 2022-11-21 | 09/02/2022 |  | Check w/ Saridha
RateManager(Prod) | Romberger, Scott | 4 | Prod |  |  |  |  | 2022-12-09 | 2022-11-21 |  |  | Y
Paceart | Tanner, Todd A | 4 | Prod |  | 11/17/2022 06:00 | 2022-12-01 | 12/01/2022 | 2022-12-09 | 2022-11-21 | 09/08/2022 |  | Y
WinAir | Yeager, B Scott | 4 | Prod |  | 11/15/2022 10:00 | 2022-11-29 | 11/29/2022 | 2022-12-09 | 2022-11-21 |  |  | Y
Communication Preferences | Violett, Dan | 4 | Prod |  | 11/15/2022 07:00 | 2022-11-29 | 11/29/2022 | 2022-12-09 | 2022-11-21 | 09/02/2022 |  | Check w/ Saridha
GHP NPI | Peters, Edward G | 4 | Prod |  | 11/15/2022 07:00 | 2022-11-29 | 11/29/2022 | 2022-12-09 | 2022-11-21 | 09/07/2022 |  | Check w/ Saridha
Hugs and Kisses | Lashock, Stanley R | 5 | Prod |  | 11/22/2022 06:00 | 2022-12-06 | 12/06/2022 | 2022-12-16 | 2022-11-28 |  |  | Y
ProGet | Shiner, Timothy | 5 | Prod |  | 11/21/2022 11:00 | 2022-12-05 | 12/05/2022 | 2022-12-16 | 2022-11-28 | 08/29/2022 |  | Y
MyAccount | Adrian Ramsay | 5 | Prod |  | 11/23/2022 11:00 | 2022-12-07 | 12/07/2022 | 2022-12-16 | 2022-11-28 |  |  | Y
Secure FTP Server | Britton, Shawn P | Net New | Non-Prod | [9 empty] | Net New
Master Provider Data Repository | Polanchyck, Greg | 1 | Non-Prod | 2022-09-26 | Cancelled | 2022-10-21 |  | 2022-10-28 | 2022-10-10 |  |  |  | Moved to Wave 5
Master Provider Data Repository | Polanchyck, Greg | 2 | Non-Prod | 2022-09-26 | Cancelled | 2022-11-02 |  | 2022-11-09 | 2022-10-20 |  |  |  | Moved to Wave 5